## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-swen-261-04-h Monkey Mode
Testing Team Name | 225-swen-261-04-f The Crimson Paragons

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Buyer I want to be able to manage their cart so that they can easily buy products. | When on product pg, should take 1 click to move item to cart | Fail | SM; Not started | Pass | DH; 4/5
| When on cart pg, should take 1-2 clicks to remove an item from the cart | Fail | SM; Not started | Pass | DH; 4/5
| Purchase/Buy button should open to a new page that would be a buying page | Fail | SM; Not started | Pass | DH; 4/5
| When an item is purchased, stocks should be lowered accordingly | Fail | SM; Not started | Fail | DH; 4/5, No purchase option
| Cart should be persistant between logging in to the same account | Fail | SM; Not started | Pass | SM 4/4: add to WL functionality works
As a buyer, I want to be able to see all the products so I can choose what I want to buy. | Home page should default sort by item IDs | Pass | SM; | Pass | DH; 4/5
| Search bar first shows all matching products, further sorted by ID | Pass | SM; | Pass | DH; 4/5; Requires two characters to be entered before it works
| After search, below matching items, a second list should be present that uses the home page default sorting | Pass | SM; | Pass | DH; 4/5
| Product pg (when user) should display Name, Item Desc., Price, and Reviews (sorted by recent) | Fail | SM; Not started | Pass | JS 4/2: UI improvement to the product page DH; 4/5
| Important info on product pg should be big enough to be easily seen by user | Fail | SM; Not started | Pass | DH; 4/5
As a Owner I want to be able to maintain inventory so that buyers can see what products are available. | To add product, need to take in name, price, item desc., species, family, and stock | Pass | SM; | Pass | DH; 4/5 (Update test desc please)
| (Not including text boxed) Should take 2-3 clicks total | Pass | SM; | Pass | DH; 4/5
| 1-2 click removal from item storage | Pass | SM; | Pass | DH; 4/5; Does not update automatically, requires refresh
| Deleted items are never lost, instead they are archived | Fail | SM; Not started | Fail | DH; 4/5; Just doesnt do it
| Item desc., Stock, and price should be updatable at any time | Fail | SM; Not started | Fail | DH; 4/5; Just doesnt do it
As a Buyer I want to be able to apply a discount code so that I can save money on my purchases. | We should have a single file that holds all active codes, 1 per line
Every discount code should have format {strCode, intPercentage} [Could be changed to floatPercentage]
Takes one click to apply previously typed in code
Text box to input discount code should be present on cart page
Discount codes should be limited to one per transaction
As a Buyer, I want to be able to add items to a wishlist (WL) so that I can purchase them at a later date | When on product pg, should take 1 click to move item to WL | Fail | SM; Not started | Pass | DH; 4/5
| Should take 1 click to remove item from WL | Fail | SM; Not started | Pass | DH; 4/5 (Autorefresh pls)
| Should take 1 click to move item from WL to cart | Fail | SM; Not started | Pass | DH; 4/5 (Autorefresh pls)
| WL should be persistant between logging in to the same account | Fail | SM; Not started | Pass | DH; 4/5
As a Buyer I want to be able to make reviews, so I can express my opinions. | When on product page, should take 2-4 clicks to post a review (not including text boxes)
Text box should be present for review entry, as well as a 1-5* drop down to post rating
Text review is optional, rating 1-5* is required to post
When logged onto the same account, reviews should be able to be edited
Admins need to have the ability to delete reviews
Deleting a review should take up to 2 clicks
(Optional) Separate file of prohibited word to auto-censor